## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02 .Database | 2.01 | Create a Product list | Implement validation on fields to ensure accurate modifications: Product name should match product type. | 2022-02-18 | 2022-02-19 | 100% | Daksh Jasani
2 | 02 .Database | 2.01 | Create a Product list | Crosscut: Product type | 2022-02-18 | 2022-02-19 | 100% | Aayushi Shah
3 | 02 .Database | 2.01 | Create a Product list | Crosscut: GUI Features | 2022-02-18 | 2022-02-19 | 100% | Elsa Poonawala
4 | 02 .Database | 2.01 | Create a Product list | Product list should be accurate for sorting | 2022-02-19 | 2022-02-20 | 100% | Shreya Niphade
5 | 02 .Database | 2.01 | Create a Product list | Execute test cases and document the text execution log | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
6 | 02 .Database | 2.02 | Update a Product list | Update product list design to be user friendly | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
7 | 02 .Database | 2.02 | Update a Product list | Execute test cases and document the text execution log | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
8 | 02 .Database | 2.02 | Update a Product list | Crosscut: Product type | 2022-02-21 | 2022-02-22 | 100% | Ajay Gupta
9 | 02 .Database | 2.02 | Update a Product list | Crosscut: GUI Features | 2022-02-21 | 2022-02-22 | 100% | Ajay Gupta
10 | 02 .Database | 2.02 | Update a Product list | Test cases for user usability | 2022-02-23 | 2022-02-24 | 100% | Daksh Jasani
11 | 02 .Database | 2.03 | Sort a Product list | Crosscut: Product type | 2022-02-25 | 2022-02-27 | 100% | Daksh Jasani
12 | 02 .Database | 2.03 | Sort a Product list | Crosscut: GUI Features | 2022-02-25 | 2022-02-26 | 100% | Noah Weitz
13 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by price | 2022-02-25 | 2022-02-26 | 100% | Darsh Jalan
14 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by price and documented test execution log | 2022-02-25 | 2022-02-26 | 100% | Aayushi Shah
15 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by size | 2022-02-26 | 2022-02-27 | 100% | Elsa Poonawala
16 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by size and documented test execution log | 2022-02-26 | 2022-02-27 | 100% | Ajay Gupta
17 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by weight | 2022-02-26 | 2022-02-27 | 100% | Shreya Niphade
18 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by weight and documented test execution log | 2022-02-27 | 2022-02-28 | 100% | Darsh Jalan
19 | 02 .Database | 2.03 | Sort a Product list | Optimize website to be more user friendly and functional | 2022-02-18 | 2022-02-19 | 100% | Darsh Jalan

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02 .Database | 2.04 | Modify a Product list | Modified product list design to be user friendly | 2022-03-05 | 2022-03-07 | 100% | Elsa Poonawala
2 | 02 .Database | 2.04 | Modify a Product list | Execute test cases and document the text execution log | 2022-03-05 | 2022-03-07 | 100% | Elsa Poonawala
3 | 02 .Database | 2.04 | Modify a Product list | visibility of product once list is modified | 2022-03-06 | 2022-03-08 | 100% | Daksh Jasani
4 | 02 .Database | 2.04 | Modify a Product list | Crosscut: GUI Features | 2022-03-08 | 2022-03-10 | 100% | Daksh Jasani
5 | 02 .Database | 2.04 | Modify a Product list | It should be intuitive and accessible for the user( not customer) to modify the product list | 2022-03-10 | 2022-03-12 | 100% | Noah Weitz
6 | 03. Advertising | 3.03 | Match similar products | Advertise product should appear after every few regular product listing | 2022-03-12 | 2022-03-14 | 100% | Ajay Gupta
7 | 03. Advertising | 3.03 | Match similar products | Click on the advertised product redirects you to offical product website | 2022-03-14 | 2022-03-16 | 100% | Ajay Gupta
8 | 03. Advertising | 3.03 | Match similar products | Visual identifier that clearly identify it as an advertisement | 2022-03-16 | 2022-03-18 | 100% | Noah Weitz
9 | 03. Advertising | 3.03 | Match similar products | Test cases for user visibility that it is an advertisement | 2022-03-15 | 2022-03-17 | 100% | Darsh Jalan
10 | 03. Advertising | 3.03 | Match similar products | Can't add advertisement to a favourite list | 2022-03-18 | 2022-03-20 | 100% | Darsh Jalan
11 | 03. Advertising | 3.03 | Match similar products | Crosscut: GUI Features | 2022-03-19 | 2022-03-21 | 100% | Shreya Niphade
12 | 04. Question and query | 4.01 | Question creation | Identifying the customer requirement | 2022-03-20 | 2022-03-22 | 100% | Aayushi Shah
13 | 04. Question and query | 4.01 | Question creation | making question jargon free | 2022-03-21 | 2022-03-23 | 100% | Aayushi Shah
14 | 04. Question and query | 4.01 | Question creation | identifying how questions should be implemented | 2022-03-22 | 2022-03-23 | 100% | Shreya Niphade
15 | 04. Question and query | 4.01 | Question creation | researching the algorithm for question implementation | 2022-03-22 | 2022-03-23 | 100% | Ajay Gupta
16 | 04. Question and query | 4.01 | Question creation | Test case: Questions should be easily understandable by layman | 2022-03-24 | 2022-03-25 | 100% | Darsh Jalan

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 03. Advertising | 3.02 | Deal/Listing Creation | Implement GUI | 2022-04-02 | 2022-04-05 | 95% | Daksh Jasani
2 | 03. Advertising | 3.02 | Deal/Listing Creation | Implement Core Functionality | 2022-04-02 | 2022-04-05 | 80% | Aayushi Shah
3 | 03. Advertising | 3.02 | Deal/Listing Creation | Implement Entitlements | 2022-04-02 | 2022-04-05 | 0% | Darsh Jalan
4 | 03. Advertising | 3.02 | Deal/Listing Creation | Develop test cases for GUI, core functionality and Entitlements | 2022-04-02 | 2022-04-05 | 85% | Shreya Niphade
5 | 03. Advertising | 3.02 | Deal/Listing Creation | Execute test cases | 2022-04-02 | 2022-04-05 | 99% | Daksh Jasani
6 | 05. Recommedation | 5.01 | Sorting through database | Implement GUI | 2022-04-03 | 2022-04-06 | 90% | Ajay Gupta
7 | 05. Recommedation | 5.01 | Sorting through database | Implement Core Functionality | 2022-04-03 | 2022-04-06 | 90% | Darsh Jalan
8 | 05. Recommedation | 5.01 | Sorting through database | Implement Entitlements | 2022-04-03 | 2022-04-06 | 0% | Daksh Jasani
9 | 05. Recommedation | 5.01 | Sorting through database | Develop test cases for GUI, core functionality and Entitlements | 2022-04-03 | 2022-04-06 | 90% | Daksh Jasani
10 | 05. Recommedation | 5.01 | Sorting through database | Execute test cases | 2022-04-03 | 2022-04-06 | 90% | Noah Weitz
11 | 05. Recommedation | 5.03 | Showing sponsored devices | Implement GUI | 2022-04-04 | 2022-04-07 | 100% | Elsa Poonawala
12 | 05. Recommedation | 5.03 | Showing sponsored devices | Implement Core Functionality | 2022-04-04 | 2022-04-07 | 100% | Ajay Gupta
13 | 05. Recommedation | 5.03 | Showing sponsored devices | Develop test cases for GUI, core functionality | 2022-04-04 | 2022-04-07 | 100% | Darsh Jalan
14 | 05. Recommedation | 5.03 | Showing sponsored devices | Execute test cases | 2022-04-04 | 2022-04-07 | 100% | Shreya Niphade