## Road Map
Tech Selector
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/04/22 | Iteration 2 - 04/01/22 | Iteration 3 - 04/22/22 | Iteration 4 - 05/13/22
Module 1 - User's Account | 01.01 Create an Account
01.02 Sign into Account
01.03 Modify User's General Information
| 01.04 Review Previous Recommendation | 3 |  |  | X
| 01.05 Ability to update/close/resolve tickets | [5 empty] | Features implemented Last Semester
01.06 Delete an Account
Module 2 - Product Lists | 02.01 Create a product lists | 3 | X
| 02.02 Update a product lists | 2 | X
| 02.03 Sort a product lists | 2 | X
| 02.04 Modify a product lists | 3 |  | X
Module 3 - Advertising | 03.01 User's historical and statistical data
| 03.02 Deal/listing Creation | 1 |  |  | X
| 03.03 Match similar products | 2 |  | X
| 03.04 Advertisement Payment and discount | 4 |  |  |  | X
Module 4 - Questions and Queries | 04.01 Question creation | 3 |  | X
| 04.02 Questions to Queries Conversion | 2 |  |  |  | X
Module 5 - Recommendation | 05.01 Sorting through database | 2 |  |  | X
| 05.02 Showing recommended devices | 3 |  |  |  | X
| 05.03 Showing sponsored devices | 3 |  |  | X
|  | VELOCITY: | 7 | 8 | 9 | 9

## Story Map
Epics |  | Tech Selector
Epic 1 - User's Account |  | Epic 1 - User's Account | Epic 2 - Product Lists | Epic 3 - Advertising | Epic 4 - Questions and Queries | Epic 5 - Recommendation
Epic 2 - Product Lists | User Stories |  | 02.01 Create a product lists
Epic 3 - Advertising |  |  | 02.02 Update a product lists
Epic 4 - Questions and Queries |  |  | 02.03 Sort a product lists |  |  |  | Iteration 1
|  |  | 02.04 Modify a product lists | 03.03 Match similar products | 04.01 Question creation
Iteration 2
|  | 01.04 Review Previous Recommendation |  | 03.02 Deal/listing Creation |  | 05.01 Sorting through database
05.03 Showing sponsored devices
Iteration 3
|  |  |  | 03.04 Advertisement Payment and disount | 04.02 Questions to Queries Conversion | 05.02 Showing recommended devices
Iteration 4