## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02 .Database | 2.01 | Create a Product list | Implement validation on fields to ensure accurate modifications: Product name should match product type. | 2022-02-18 | 2022-02-19 | 100% | Daksh Jasani
2 | 02 .Database | 2.01 | Create a Product list | Crosscut: Product type | 2022-02-18 | 2022-02-19 | 100% | Aayushi Shah
3 | 02 .Database | 2.01 | Create a Product list | Crosscut: GUI Features | 2022-02-18 | 2022-02-19 | 100% | Elsa Poonawala
4 | 02 .Database | 2.01 | Create a Product list | Product list should be accurate for sorting | 2022-02-19 | 2022-02-20 | 100% | Shreya Niphade
5 | 02 .Database | 2.01 | Create a Product list | Execute test cases and document the text execution log | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
6 | 02 .Database | 2.02 | Update a Product list | Update product list design to be user friendly | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
7 | 02 .Database | 2.02 | Update a Product list | Execute test cases and document the text execution log | 2022-02-19 | 2022-02-20 | 100% | Daksh Jasani
8 | 02 .Database | 2.02 | Update a Product list | Crosscut: Product type | 2022-02-21 | 2022-02-22 | 100% | Ajay Gupta
9 | 02 .Database | 2.02 | Update a Product list | Crosscut: GUI Features | 2022-02-21 | 2022-02-22 | 100% | Ajay Gupta
10 | 02 .Database | 2.02 | Update a Product list | Test cases for user usability | 2022-02-23 | 2022-02-24 | 100% | Daksh Jasani
11 | 02 .Database | 2.03 | Sort a Product list | Crosscut: Product type | 2022-02-25 | 2022-02-27 | 100% | Daksh Jasani
12 | 02 .Database | 2.03 | Sort a Product list | Crosscut: GUI Features | 2022-02-25 | 2022-02-26 | 100% | Noah Weitz
13 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by price | 2022-02-25 | 2022-02-26 | 100% | Darsh Jalan
14 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by price and documented test execution log | 2022-02-25 | 2022-02-26 | 100% | Aayushi Shah
15 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by size | 2022-02-26 | 2022-02-27 | 100% | Elsa Poonawala
16 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by size and documented test execution log | 2022-02-26 | 2022-02-27 | 100% | Ajay Gupta
17 | 02 .Database | 2.03 | Sort a Product list | Implemented functionality for sorting by weight | 2022-02-26 | 2022-02-27 | 100% | Shreya Niphade
18 | 02 .Database | 2.03 | Sort a Product list | Tested functionality for sorting by weight and documented test execution log | 2022-02-27 | 2022-02-28 | 100% | Darsh Jalan
19 | 02 .Database | 2.03 | Sort a Product list | Optimize website to be more user friendly and functional | 2022-02-18 | 2022-02-19 | 100% | Darsh Jalan